## Sheet1
|  | Project: Warhammer 40k Unit Efficiency Calculator - Timeline |  |  |  | Milestone 1 |  | Milestone 2 |  |  | Milestone 3 |  |  | Milestone 4
Key | [5 empty] | Project Description/ |  | Planning and Documentation |  |  | Development of Calculator |  |  | System complete
Frederick - Developer / Marketing | [5 empty] | Requirement Complete |  | Complete. |  |  | Functions Complete
Dan - Developer / Test Engineer
Winson - Developer / Test Engineer
Anthony - Developer/Reqs. Analyst
All
Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
Project Description
Project Elicitation
Functional Requirements
Confirm Stakeholder Needs
40K Rules Tutorials
Java Tutorials for Mobile
Create Function Documentation
App Layout/Design Mockup
Contruct Psuedocode
ModifierConvert Function
StrvTgh Function
ToHitFunc
ToWoundFunc
DamageFunc
RandomDamange Func
Add Error Handling
Develop User Interface
Connect Functions with Interface
Test Application